## Sheet1
Date | Quality of work (1-10) | Time worked | Comments
2018-06-18 | 2018-10-09 | 2:00 | Finished project proposal, now moving on to End user surveys
2018-06-20 | 2018-10-07 | 0:50 | Began designing the end user survey. Quality of work was dampened by an inability to understand the task towards the beginning.
End user survey questions have been established, as well as the purpose of the survey
2018-07-10 | 2018-10-06 | 2:00 | Three weeks behind due to illness, must work hard within the next few weeks to catch up on backlog, finished End user survey analysis
2018-07-17 | 2018-10-04 | 0:30 | Four weeks behind due to a broken computer, MUST work hard within the next few weeks to catch up on backlog, began feasibility study.
2018-07-19 | 2018-10-06 | 0:30 | Finished feasibility study, will do ~2hrs of work on 21/07/18
2018-07-21 | 2018-10-06 | 0:30 | Published end user survey
2018-07-29 | 2018-10-08 | 3:00 | Halfway through Detailed project plan, continuing on 31/08/2018
2018-08-21 | 2018-10-06 | 0:50 | continued detailed project plan
2018-08-23 | 2018-10-07 | 2:30 | Finished detailed project plan, started planning for test plan/Requirements specifications
2018-10-24 | 2018-10-08 | 1:00 | Finished requirements specifications. Took a month's break due to stress + other factors. Working hard from here on out.
2018-10-25 | 2018-10-06 | 0:30 | Started test plan, did first page
2018-10-26 | 2018-10-06 | 0:30 | Finished test plan, including input validation.
2018-10-29 | 2018-10-07 | 0:30 | Researched potential wireframe programs. Decided on invision
2018-10-30 | 2018-10-06 | 1:00 | Finished first draft of wireframe of Main menu
2018-10-31 | 2018-10-06 | 1:00 | Finished first draft of wireframe of 'Esc' menu
2018-10-01 | 2018-10-06 | 1:00 | Finished first draft of wireframe of start menu
2018-11-06 | 2018-10-08 | 1:00 | Began pseudocode and implementation, main menu was begun
2018-11-07 | 2019-10-05 | 2:00 | Very little progress made, struggling with implementation of main menu. Continued pseudocode in tandem.
2018-11-08 | 2019-10-04 | 2:00 | Continued pseudocode design and implementation, struggling with translating pseudocode concepts to pygame.
2018-11-09 | 2019-10-08 | 2:00 | Text and button classes made. Progress made. main function began to be implemented including quit function. Pseudocode for main menu finished.
2018-11-16 | 2019-10-08 | 1:00 | buttons made functional and began implementation of main game and pseudocode of main game, including movement of sprites and loading game
2018-11-23 | 2019-10-07 | 2:00 | animated sprites masks made, soon to be implemented.
2018-11-24 | 2019-10-07 | 2:00 | pseudocode of sprite class created and implemented, considering how to animate sprites
25/11//2018 | 2019-10-08 | 2:00 | began on 'enemy ball' class AKA test class to test how sprite animation works
2018-11-26 | 2019-10-03 | 1:00 | Continued on spriteAnimate function deisgn. Struggling with translation.
2018-11-27 | 2019-10-04 | 1:00 | continued to struggle with spriteAnimate
2018-11-28 | 2019-10-07 | 2:00 | Breakthrough - got correct pseudocode and sprite animation.
2018-12-15 | 2019-10-06 | 1:00 | Finished animation of mainsprite class design and implementation, began movement code.
2018-12-16 | 2019-10-07 | 1:00 | Finished movement code design and implementation. This messed up sprite animation, gravity to be implemented and bugs to be fixed
2018-12-17 | 2019-10-08 | 2:00 | Bug fixed. Gravity to be implemented and designed next
2019-02-15 | 2019-10-05 | 1:00 | Gravity design started
2019-02-17 | 2019-10-06 | 2:00 | Gravity implementation started, struggling
2019-02-18 | 2019-10-04 | 2:00 | Gravity implementation failing
2019-02-19 | 2019-10-04 | 2:00 | gravity implementation not working
2019-02-20 | 2019-10-03 | 2:00 | Gravity implementation not working
2019-02-21 | 2019-10-03 | 2:00 | Decided on new project as deadline is in one month and implementation would take a few months. Started maze game.
2019-03-01 | 2019-10-06 | 1:00 | Project proposal for maze project began and finished
2019-03-02 | 2019-10-05 | 1:00 | Research of feasibility completed and end user survey published. Project plan outline finished. Detailed project plan (Gantt Chart) finished
2019-03-03 | 2019-10-08 | 2:00 | Finished analysis of End user Survey and began Requirements Specifications
2019-03-04 | 2019-10-08 | 4:00 | Changed project proposal slightly as it didn't have the details of the end user group on it. As well as this it didn't have extra details on methods for deliverables
Finished requirements specifications.
2019-03-05 | 2019-10-05 | 2:00 | Worked on Test Plan
2019-03-06 | 2019-10-07 | 3:00 | Finished test plan, including input validation and integration testing.
2019-03-07 | 2019-10-08 | 4:00 | Finished user interface design (See justifications for further info)
2019-03-08 | 2019-10-08 | 3:00 | Began data flow design
2019-03-13 | 2019-10-08 | 2:00 | Started pseudocode and implementation of maze game. Used main menu from previous game for the maze game, replacing 'blue' with 'maze', maze class finished. Started working on mainSprite class
2019-03-14 | 2019-10-07 | 2:00 | Tested the main menu component. two iterations of design/implementation/testing completed. Finished testing maze component, two iterations completed.
2019-03-15 | 2019-10-09 | 2:00 | finished mainSprite movement, collision and winning. Tested player input (three iterations), collision detection (one iteration), input validation (one iteration).
Testing of maze class was completed, two iterations of design/implementation/testing completed.
2019-03-16 | 2019-10-10 | 2:00 | inGame menu has close and open() methods, and is finished. Loadgame/savegame functions completed. Keys function completed,mazeone subclass finished. All classes and functions are integrated and tested (Three iterations).
Finished component testing for in-game menu testing (two iterations),save/load testing (one iteration) and integration testing (three iterations)
2019-03-27 | 2019-10-06 | 1:00 | Started and finished evaluation
2019-03-28 | 2019-10-10 | 4:00 | Finished data dump (compiling code into one document)